## Task_Table
ID | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Project Overview, Literature Review, Survey, Feature and technology list, Technology overview | 1 Week | 2015-05-01 | 2015-10-01
2 | Database, Sitewide modules overview, Users | 1 Week | 2015-12-01 | 17/1/2015
3 | Initial site and database setup, Login module, administrator and sitewide validation | 1 Week | 19/1/2015 | 24/1/2015
4 | Manager module, Publisher module | 1 Week | 26/1/2015 | 31/1/2015
5 | Sitewide security checkup and sitewide php,css and javascript optimization | 1 Week | 2015-02-02 | 2015-07-02
6 | Updation in Database, Creation of Change Password Script. | 1 Week | 2015-09-02 | 14/2/2015
7 | Comparison with Laravel Framework, Preparation for upload scripts for assets. | 1 Week | 16/2/2015 | 21/2/2015
8 | Encryption and Decryption, Creation of Asset Module. | 1 Week | 23/2/2015 | 28/2/2015
9 | Creation of Forms | 1 Week | 2015-02-03 | 2015-07-03
10 | Creation of Background Themes | 1 Week | 2015-09-03 | 14/3/2015
11 |  | 1 Week | 16/3/2015 | 21/3/2015
12 |  | 1 Week | 23/3/2015 | 28/3/2015
13 |  | 1 Week | 30/3/2015 | 2015-04-04
14 |  | 1 Week | 2015-06-04 | 2015-11-04
15 |  | 1 Week | 13/4/2015 | 18/4/2015
16 |  | 1 Week | 20/4/2015 | 25/4/2015
17 |  | 1 Week | 27/4/2015 | 2015-02-05
18 |  | 1 Week | 2015-04-05 | 2015-09-05
19 |  | 1 Week | 2015-11-05 | 16/5/2015
20 |  | 1 Week | 18/5/2015 | 23/5/2015
21 |  | 1 Week | 25/5/2015 | 30/5/2015
22 |  | 1 Week | 2015-01-06 | 2015-06-06
23 |  | 1 Week | 2015-08-06 | 13/6/2015
24 |  | 1 Week | 15/6/2015 | 20/6/2015
25 |  | 1 Week | 22/6/2015 | 27/6/2015

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units

## Info_Table
Microsoft Project | Template ID: | 9876543210 | (Do Not Edit)
Microsoft Project is a project management program designed to help you plan and manage your projects and communicate project information.
Whether you have a simple list of tasks or want to coordinate activities across multiple projects, Microsoft Project makes it easy to get started and learn as you go.
With this template you can export data to Excel to perform more advanced numerical analysis. Then you can import project data back into Microsoft Project to perform standard project tasks, such as:
* Seeing your tasks linked in a Gantt Chart
* Seeing how much work each person on the team has assigned to them
You can easily import this information back into Microsoft Project and keep working without reentering data.